## Development(180)
Cost Breakdown for Item A Development of Steel Welding VR Training (30 Minutes)
Sl. | Departments | Heads | Type | No. of Unit | No. of Days | Per Day Cost | Unit Cost | Total Cost
1 | Managing & Planning Department | Project Manager | Senior | 1 | 20 | 5653.16 | 113063.2 | 174154.12
|  | Product Designer | Senior | 1 | 12 | 5090.91 | 61090.92
2 | Art Department | UI/UX Designer | Senior | 1 | 10 | 5272.73 | 52727.3 | 1300727.46
|  | 3D Artist | Senior | 2 | 66 | 6000 | 792000
|  | 2D Artist | Senior | 2 | 44 | 5181.82 | 456000.16
3 | Development Department | Technical Lead | Senior | 1 | 10 | 7251.41 | 72514.1 | 1977287.1
|  | Devops | Senior | 1 | 5 | 6090.91 | 30454.55
|  | VR Developer | Senior | 3 | 75 | 6590.91 | 1482954.75
|  | Backend Developer | Senior | 2 | 35 | 5590.91 | 391363.7
| Others | QA Expert (Test Engineer) | Senior | 1 | 12 | 4590.91 | 55090.92 | 101181.84
4 |  | QA Expert (Test Engineer) | Mid | 1 | 12 | 3840.91 | 46090.92
Total | [7 empty] | 3553350.52
Note: Development Timeline = 4 Months

## Development (90)
Cost Breakdown for Item A Development of Steel Welding VR Training (90 Minutes)
Sl. | Departments | Heads | Type | No. of Unit | No. of Days | Per Day Cost | Unit Cost
1 | Managing & Planning Department | Project Manager | Senior | 1 | 20 | 5653.16 | 113063.2 | 174154.12
|  | Product Designer | Senior | 1 | 12 | 5090.91 | 61090.92
2 | Art Department | UI/UX Designer | Senior | 1 | 10 | 5272.73 | 52727.3 | 1075454.7
|  | 3D Artist | Senior | 2 | 55 | 6000 | 660000
|  | 2D Artist | Senior | 2 | 35 | 5181.82 | 362727.4
3 | Development Department | Technical Lead | Senior | 1 | 10 | 7251.41 | 72514.1 | 1168650.62
|  | Devops | Senior | 1 | 5 | 6090.91 | 30454.55
|  | VR Developer | Senior | 2 | 66 | 6590.91 | 870000.12
|  | Backend Developer | Senior | 1 | 35 | 5590.91 | 195681.85
| Others | QA Expert (Test Engineer) | Senior | 1 | 12 | 4590.91 | 55090.92 | 101181.84
4 |  | QA Expert (Test Engineer) | Mid | 1 | 12 | 3840.91 | 46090.92
Total | [7 empty] | 2519441.28
Note: Development Timeline = 3.5 Months

## Development (60)
Cost Breakdown for Item A Development of Steel Welding VR Training (90 Minutes)
Sl. | Departments | Heads | Type | No. of Unit | No. of Days | Per Day Cost | Unit Cost
1 | Managing & Planning Department | Project Manager | Senior | 1 | 20 | 5653.16 | 113063.2 | 174154.12
|  | Product Designer | Senior | 1 | 12 | 5090.91 | 61090.92
2 | Art Department | UI/UX Designer | Senior | 1 | 10 | 5272.73 | 52727.3 | 564091
|  | 3D Artist | Senior | 1 | 55 | 6000 | 330000
|  | 2D Artist | Senior | 1 | 35 | 5181.82 | 181363.7
3 | Development Department | Technical Lead | Senior | 1 | 10 | 7251.41 | 72514.1 | 817514.21
|  | Devops | Senior | 1 | 5 | 6090.91 | 30454.55
|  | VR Developer | Senior | 1 | 66 | 6590.91 | 435000.06
|  | Backend Developer | Senior | 1 | 50 | 5590.91 | 279545.5
| Others | QA Expert (Test Engineer) | Senior | 1 | 12 | 4590.91 | 55090.92 | 101181.84
4 |  | QA Expert (Test Engineer) | Mid | 1 | 12 | 3840.91 | 46090.92
Total | [7 empty] | 1656941.17
Note: Development Timeline = 2.5 Months

## Development (30)
Cost Breakdown for Item A Development of Steel Welding VR Training (90 Minutes)
Sl. | Departments | Heads | Type | No. of Unit | No. of Days | Per Day Cost | Unit Cost
1 | Managing & Planning Department | Project Manager | Senior | 1 | 10 | 5653.16 | 56531.6 | 97258.88
|  | Product Designer | Senior | 1 | 8 | 5090.91 | 40727.28
2 | Art Department | UI/UX Designer | Senior | 1 | 8 | 5272.73 | 42181.84 | 336181.88
|  | 3D Artist | Senior | 1 | 30 | 6000 | 180000
|  | 2D Artist | Senior | 1 | 22 | 5181.82 | 114000.04
3 | Development Department | Technical Lead | Senior | 1 | 8 | 7251.41 | 58011.28 | 403102.24
|  | Devops | Senior | 1 | 4 | 6090.91 | 24363.64
|  | VR Developer | Senior | 1 | 30 | 6590.91 | 197727.3
|  | Backend Developer | Senior | 1 | 22 | 5590.91 | 123000.02
4 | Others | QA Expert (Test Engineer) | Senior | 1 | 8 | 4590.91 | 36727.28 | 36727.28
Total | [7 empty] | 873270.28
Note: Development Timeline = 1.5 Months