## Development
Develop and Deliver Two E-Learning Courses on Digital Accessibility and Disability
Sl. | Departments | Heads | Type | No. of Unit | No. of Days | Per Day Cost | Unit Cost | Total Cost
1 | Managing & Planning Department | Project Manager | Senior | 1 | 10 | 5653.16 | 56531.6 | 56531.6
2 | Art Department | Creative Director | Senior | 1 | 16 | 6340.91 | 101454.56 | 739763.7
|  | Graphics Designer | Senior | 1 | 22 | 5209.09 | 114599.98
|  | Motion Graphics Designer | Senior | 2 | 28 | 5209.09 | 291709.04
|  | Illustrator | Senior | 2 | 22 | 5272.73 | 232000.12
4 | Others | Script Writer | Senior | 1 | 16 | 3590.91 | 57454.56 | 203409.14
|  | Voice Artist | Senior | 1 | 18 | 3840.91 | 69136.38
|  | Trainer | Senior | 1 | 20 | 3840.91 | 76818.2
Total | [7 empty] | 999704.44
Note: Development Timeline = 2.5 months